# Chesapeake Tree Canopy Outcome –Management Board SRS Review

Contact/questions: Julie Mawhorter, jmawhorter@fs.fed.us

6/6/2018 Forestry Workgroup Update – see posted materials

Background & Process

- Each outcome in the CB Watershed Agreement goes through a Biennial Strategy Review System (SRS) process with the Management Board (MB) – ours is scheduled for Nov. 15, 2018

- Our Tree Canopy SRS review will be part of the “Local Action” cohort, including also Local Leadership, Land Use Methods and Metrics, and Land Use Options Evaluation

- As part of the review process in the months ahead we will:

  - Review and update the status of our 2 Year Workplan within the new logic table template (See posted 2015-2017 Tree Canopy Workplan -To Be Updated)

  - Prepare/review data related to our Tree Canopy outcome – indicator, baseline, progress as reflected in BMPs reported (See posted Tree Canopy Indicator Proposal draft)

  - Consider guiding questions/issues affecting our progress: Assumptions/Factors Influencing outcome; Current Efforts and Gaps; Management Actions; Challenges & Adaptation recommended

  - Hone in on the most critical issues/needs/questions for MB consideration to guide our actions ahead and motivate partnership action – prepare a compelling, concise presentation for Nov. 15

  - Taking MB, FWG and stakeholder input into account, revise/release next 2 Year Workplan and revise Tree Canopy Management Strategy as needed (~120 day process following Nov. 15)

Timeline – Key Dates

  - June 28 – Tree Canopy planning/strategy meeting with state leads (Annapolis CBP, 10-3)

  - July 15 – Comments due on Tree Canopy Indicator Proposal

  - Sept. 5 – Forestry Workgroup meeting (face to face), Annapolis TBD 10-3 ; invite stakeholder participation

  - Oct. 18 + 26 – Draft and Final presentation materials for Management Board review due

  - Nov. 15 –  Tree Canopy SRS Review with Management Board

  - Nov. 28 – Follow up materials/requests due to Management Board

  - Dec. 6 – Follow up Management Board meeting

  - Mar. 14 – Submit revised Tree Canopy Management Strategy and 2-Year Workplan to MB (Covering March 2019-Nov. 2020)

Related Resources:

Tree Canopy Management Strategy and 2-Year Workplan – CBP Website

CBP SRS Review Materials – all outcomes

Chesapeake Tree Canopy Network (our partnership website)