## Draft Table
Forage Outcome | Continually improve the Partnership’s capacity to understand the role of forage fish populations in the Chesapeake Bay. By 2016, develop a strategy for assessing the forage fish base available as food for predatory species in the Chesapeake Bay.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | Critical Action
e.g.: Use Conflict: Limited financial resources | e.g.: Fish Passage Workgroup will need more than $20 million in project implementation funds in order to meet Outcome | e.g.: Prioritize dam removal projects to ensure the strategic investment of public funds | e.g.: Identify high-priority watersheds in MD, PA and VA in which to focus fish passage efforts | e.g.: Fish Passage Workgroup | e.g.: X
Public Engagement | Public knowledge can be improved to expand understanding of forage in the Chesapeake Bay and the importance of considering trophic relationships when managing fisheries. | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.3): Conduct outreach to emphasize importance of forage species and the application of efforts to quantify their role in the Bay ecosystem. | Sustainable Fisheries GIT Staff, Forage Action Team
Landowner Engagement | Landowners can add value to the partnership by understanding the importance of forage in the Chesapeake Bay and learning how they can make decisions on their property that can enhance or protect nearby forage habitat (e.g. building a living shoreline, reducing use of pesticides, planting trees along stream edges) | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.3): Conduct outreach to emphasize importance of forage species and the application of efforts to quantify their role in the Bay ecosystem. | Sustainable Fisheries GIT Staff, Forage Action Team
Legislative Engagement at the Federal, State and/or Local Levels | Jurisdictions have not established forage legislation at this time. Based on further research, fishery managers can assess what or how legislation should be enacted to maintain sustainable forage populations. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups | X
Government Agency Engagement at the Federal, State and/or Local Levels | Fishery managers have limited resources to dedicate to forage management, therefore prioritized forage species need to be defined to direct future efforts. | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.1): Using results from the forage workshop report, Fisheries GIT resources managers will identify highest priority forage species to focus near-term science and management efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) | X
|  |  | WP Action (1.2): Resource managers will identify and prioritize forage species from the forage workshop report to focus long term efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) | X
|  |  | WP Action (1.3): Conduct outreach to emphasize importance of forage species and the application of efforts to quantify their role in the Bay ecosystem. | Sustainable Fisheries GIT Staff, Forage Action Team
| Forage metrics or indicators are needed to monitor progress as fishery managers develop plans or objectives to manage for a sustainable forage population. | Management Approach (2): Determine the status of the forage base including a definition of a "balanced" state. | WP Action (2.1): Use existing data to develop indicators and metrics for near-term species. | Forage Action Team, MD DNR, VMRC, PRFC, UMCES | X
|  |  | WP Action (2.2): Develop a definition of a "balanced" state for predators and prey. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), UMCES | X
| Management jurisdictions need further data to establish management objectives for priority forage. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups | X
Nongovernmental Organization Engagement | Nongovernmental organizations can offer input on priority forage and indicate where their objectives align with government agency objectives. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups | X
| Nongovernmental organizations have access to extensive citizen monitoring efforts which can assist in closing monitoring gaps. | Management Approach (4): Maximize the efficiency of monitoring programs and build on existing efforts. | WP Action (4.1): Identify and prioritize monitoring gaps for forage species | Forage Action Team, STAR, MD DNR, VIMS
Partner Coordination | Partner coordination and collaboration is needed to identify priority species and find innovative and effective methods of reaching out to stakeholders in the Chesapeake Bay. | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.1): Using results from the forage workshop report, Fisheries GIT resources managers will identify highest priority forage species to focus near-term science and management efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) | X
|  |  | WP Action (1.2): Resource managers will identify and prioritize forage species from the forage workshop report to focus long term efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) | X
|  |  | WP Action (1.3): Conduct outreach to emphasize importance of forage species and the application of efforts to quantify their role in the Bay ecosystem. | Sustainable Fisheries GIT Staff, Forage Action Team
| Partners can collaborate to use existing data to establish metrics that will assist the Forage Action Team in monitoring progress in achieving the Forage Outcome. | Management Approach (2): Determine the status of the forage base including a definition of a "balanced" state. | WP Action (2.1): Use existing data to develop indicators and metrics for near-term species. | Forage Action Team, MD DNR, VMRC, PRFC, UMCES | X
|  |  | WP Action (2.2): Develop a definition of a "balanced" state for predators and prey. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), UMCES | X
| Partners are needed to integrate Baywide interests into management objectives. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups | X
| Partners have access to extensive citizen monitoring efforts which can assist in closing monitoring gaps and can introduce innovative approaches in maximizing the efficiency of monitoring programs. | Management Approach (4): Maximize the efficiency of monitoring programs and build on existing efforts. | WP Action (4.1): Identify and prioritize monitoring gaps for forage species | Forage Action Team, STAR, MD DNR, VIMS
|  |  | WP Action (4.2): Draft a strategy for assessing the forage base available as food for predatory species in the Chesapeake Bay | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) | X
Scientific and Technical Understanding | Prioritization of forage species will depend on available data and tools to monitor populations and understand population dynamics of selected species. | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.1): Using results from the forage workshop report, Fisheries GIT resources managers will identify highest priority forage species to focus near-term science and management efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) | X
|  |  | WP Action (1.2): Resource managers will identify and prioritize forage species from the forage workshop report to focus long term efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) | X
| Data and consistent monitoring programs are needed to assess the status of the forage base. | Management Approach (2): Determine the status of the forage base including a definition of a "balanced" state. | WP Action (2.1): Use existing data to develop indicators and metrics for near-term species. | Forage Action Team, MD DNR, VMRC, PRFC, UMCES | X
|  |  | WP Action (2.2): Develop a definition of a "balanced" state for predators and prey. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), UMCES | X
| Management jurisdictions need further data to establish management objectives for priority forage. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups | X
| Established monitoring methodology will be essential in accurately assessing the forage base and determining trophic relationships of forage in the Chesapeake Bay. | Management Approach (4): Maximize the efficiency of monitoring programs and build on existing efforts. | WP Action (4.1): Identify and prioritize monitoring gaps for forage species | Forage Action Team, STAR, MD DNR, VIMS
|  |  | WP Action (4.2): Draft a strategy for assessing the forage base available as food for predatory species in the Chesapeake Bay | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) | X
Factors Influencing Success from Management Strategy
Habitat (amount and quality) | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Predation | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Water Quality | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Land Use and Watershed Development | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Fishing and Catch Removals | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Food for forage species | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Monitoring/Survey Costs | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Data Availability and Analysis Costs | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Baywide Coordination | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified

## Full Table
Fish Habitat Outcome | Continually improve the effectiveness of fish habitat conservation and restoration efforts by identifying and characterizing critical fish and shellfish spawning, nursery and forage areas within the Chesapeake Bay and its tributaries. Use existing and new tools to integrate information and conduct assessments to inform restoration and conservation efforts.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | How do you track whether action is complete? | Expected Response | Lesson(s) Learned | Adaptation(s) Made or Recommended | Critical Action (Indicate with an X)
e.g.: Use Conflict: Limited financial resources | e.g.: Fish Passage Workgroup will need more than $20 million in project implementation funds in order to meet Outcome | e.g.: Prioritize dam removal projects to ensure the strategic investment of public funds | e.g.: Identify high-priority watersheds in MD, PA and VA in which to focus fish passage efforts | e.g.: Fish Passage Workgroup | e.g.: High-priority watersheds identified |  |  |  | e.g.: X
Public Engagement | Public knowledge can be improved to expand understanding of forage in the Chesapeake Bay and the importance of considering trophic relationships when managing fisheries. | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.3): Conduct outreach to emphasize importance of forage species and the application of efforts to quantify their role in the Bay ecosystem. | Sustainable Fisheries GIT Staff, Forage Action Team
Landowner Engagement | Landowners can add value to the partnership by understanding the importance of forage in the Chesapeake Bay and learning how they can make decisions on their property that can enhance or protect nearby forage habitat (e.g. building a living shoreline, reducing use of pesticides, planting trees along stream edges) | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.3): Conduct outreach to emphasize importance of forage species and the application of efforts to quantify their role in the Bay ecosystem. | Sustainable Fisheries GIT Staff, Forage Action Team
Legislative Engagement at the Federal, State and/or Local Levels | Jurisdictions have not established forage legislation at this time. Based on further research, fishery managers can assess what or how legislation should be enacted to maintain sustainable forage populations. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups |  |  |  |  | X
Government Agency Engagement at the Federal, State and/or Local Levels | Fishery managers have limited resources to dedicate to forage management, therefore prioritized forage species need to be defined to direct future efforts. | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.1): Using results from the forage workshop report, Fisheries GIT resources managers will identify highest priority forage species to focus near-term science and management efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) |  |  |  |  | X
|  |  | WP Action (1.2): Resource managers will identify and prioritize forage species from the forage workshop report to focus long term efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) |  |  |  |  | X
|  |  | WP Action (1.3): Conduct outreach to emphasize importance of forage species and the application of efforts to quantify their role in the Bay ecosystem. | Sustainable Fisheries GIT Staff, Forage Action Team
| Forage metrics or indicators are needed to monitor progress as fishery managers develop plans or objectives to manage for a sustainable forage population. | Management Approach (2): Determine the status of the forage base including a definition of a "balanced" state. | WP Action (2.1): Use existing data to develop indicators and metrics for near-term species. | Forage Action Team, MD DNR, VMRC, PRFC, UMCES |  |  |  |  | X
|  |  | WP Action (2.2): Develop a definition of a "balanced" state for predators and prey. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), UMCES |  |  |  |  | X
| Management jurisdictions need further data to establish management objectives for priority forage. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups |  |  |  |  | X
Nongovernmental Organization Engagement | Nongovernmental organizations can offer input on priority forage and indicate where their objectives align with government agency objectives. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups |  |  |  |  | X
| Nongovernmental organizations have access to extensive citizen monitoring efforts which can assist in closing monitoring gaps. | Management Approach (4): Maximize the efficiency of monitoring programs and build on existing efforts. | WP Action (4.1): Identify and prioritize monitoring gaps for forage species | Forage Action Team, STAR, MD DNR, VIMS
Partner Coordination | Partner coordination and collaboration is needed to identify priority species and find innovative and effective methods of reaching out to stakeholders in the Chesapeake Bay. | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.1): Using results from the forage workshop report, Fisheries GIT resources managers will identify highest priority forage species to focus near-term science and management efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) |  |  |  |  | X
|  |  | WP Action (1.2): Resource managers will identify and prioritize forage species from the forage workshop report to focus long term efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) |  |  |  |  | X
|  |  | WP Action (1.3): Conduct outreach to emphasize importance of forage species and the application of efforts to quantify their role in the Bay ecosystem. | Sustainable Fisheries GIT Staff, Forage Action Team
| Partners can collaborate to use existing data to establish metrics that will assist the Forage Action Team in monitoring progress in achieving the Forage Outcome. | Management Approach (2): Determine the status of the forage base including a definition of a "balanced" state. | WP Action (2.1): Use existing data to develop indicators and metrics for near-term species. | Forage Action Team, MD DNR, VMRC, PRFC, UMCES |  |  |  |  | X
|  |  | WP Action (2.2): Develop a definition of a "balanced" state for predators and prey. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), UMCES |  |  |  |  | X
| Partners are needed to integrate Baywide interests into management objectives. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups |  |  |  |  | X
| Partners have access to extensive citizen monitoring efforts which can assist in closing monitoring gaps and can introduce innovative approaches in maximizing the efficiency of monitoring programs. | Management Approach (4): Maximize the efficiency of monitoring programs and build on existing efforts. | WP Action (4.1): Identify and prioritize monitoring gaps for forage species | Forage Action Team, STAR, MD DNR, VIMS
|  |  | WP Action (4.2): Draft a strategy for assessing the forage base available as food for predatory species in the Chesapeake Bay | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) |  |  |  |  | X
Scientific and Technical Understanding | Prioritization of forage species will depend on available data and tools to monitor populations and understand population dynamics of selected species. | Management Approach (1): Define forage species and what comprises the forage base. | WP Action (1.1): Using results from the forage workshop report, Fisheries GIT resources managers will identify highest priority forage species to focus near-term science and management efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) |  |  |  |  | X
|  |  | WP Action (1.2): Resource managers will identify and prioritize forage species from the forage workshop report to focus long term efforts. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) |  |  |  |  | X
| Data and consistent monitoring programs are needed to assess the status of the forage base. | Management Approach (2): Determine the status of the forage base including a definition of a "balanced" state. | WP Action (2.1): Use existing data to develop indicators and metrics for near-term species. | Forage Action Team, MD DNR, VMRC, PRFC, UMCES |  |  |  |  | X
|  |  | WP Action (2.2): Develop a definition of a "balanced" state for predators and prey. | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), UMCES |  |  |  |  | X
| Management jurisdictions need further data to establish management objectives for priority forage. | Management Approach (3): Inform management decisions to better address sustainability of the forage base. | WP Action (3.1): The management jurisdictions will establish management objectives for priority forage species(near-term and long-term) | Chesapeake Bay Commission, Sustainable Fisheries GIT Staff, Forage action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC), management agency advising groups |  |  |  |  | X
| Established monitoring methodology will be essential in accurately assessing the forage base and determining trophic relationships of forage in the Chesapeake Bay. | Management Approach (4): Maximize the efficiency of monitoring programs and build on existing efforts. | WP Action (4.1): Identify and prioritize monitoring gaps for forage species | Forage Action Team, STAR, MD DNR, VIMS
|  |  | WP Action (4.2): Draft a strategy for assessing the forage base available as food for predatory species in the Chesapeake Bay | Forage Action Team, Sustainable Fisheries GIT Executive Committee (MD, VA, PRFC) |  |  |  |  | X
Factors Influencing Success from Management Strategy
Habitat (amount and quality) | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Predation | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Water Quality | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Land Use and Watershed Development | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Fishing and Catch Removals | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Food for forage species | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Monitoring/Survey Costs | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Data Availability and Analysis Costs | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Baywide Coordination | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified