## Stream Health QPM Prep
Stream Health Outcome | Continually improve stream health and function throughout the watershed. Improve health and function of 10 percent of stream miles above the 2008 baseline for the Chesapeake Bay watershed.
Factor | Gap | Management Approach or Action | Work Plan Action | Responsible Party | Critical Action
Local Legislative Engagement: Policy maker understanding of stream restoration practices and benefits to ecosystem | Project design process for stream restoration that can measure change in stream functions and project success is based on a project goals and objectives | Management Approach (5): Work with CB Partners to include GIT 6, to enhance the capacity of local governments, organizations, and landowners of beneficial stream restoration and maintenance practices | WP Action (5.1): Provide training and education materials to local officials on stream restoration and health | SHWG, USC, TU
State Legislative Engagement: Stream restoration permitting | Delays from both the practitioner and regulator in the permit review process can hinder implementation efforts | Management Approach (3): Active and engaged participation by local communities with Federal and State partners is central to Bay restoration (see Management Strategy for full Approach). | WP Action (3.2): Develop streamlined process for permitting | SHWG, MDE, MD DNR, DC DOEE, VA DEQ
Partner Coordination: Engaging all available partners in the watershed conducting work to measure stream health | Lack of process and funding to track and report updated Chessie BIBI | Management Approach (1): Identify an appropriate suite of metrics to measure the multiple facets of stream health to complement the baywide Chessie BIBI. | WP Action (1.3): Determine and report stream health progress | All Bay States and DC, ICPRB, EPA CBP | X
Partner Coordination: Development of a shared stream restoration monitoring protocols and technical guidelines | Lack of common watershed, stressor, and stream assessment and restoration guidelines | Management Approach (2): Provision of adequate funding and technical resources to support functional lift in stream restoration projects, in addition to nutrient and sediment reduction. | WP Action (2.1): Implement pooled monitoring approach | MD, ICPRB, TU, CBT
Partner Coordination: Understanding of common permitting needs and challenges | Information needs to support innovative, effective design approaches to identify restoration potential and success for different land uses, stream types, and current and future site constraints, causes of impairment/stressors | Management Approach (3): Active and engaged participation by local communities with Federal and State partners is central to Bay restoration (see Management Strategy for full Approach). | WP Action (3.1): Develop stream restoration permit committee | USACE, EPA, MDE, VA DEQ, VMRC, Anne Arundel County, Fairfax County, PA DEP, DC DOEE, TU
Partner Coordination: Sharing of scientific understanding | Adequate extension infrastructure to communicate newest research and technical guidance to jurisdictions | Management Approach (4): Develop and promote holistic stream restoration design guidleines that identifies the level of degradation and improvement of stream functions and key stressors/factors limiting potential uplift | WP Action (4.3): Provide stream training to regulators and pracitioners | SHWG
Scientific and Technical Understanding: Develop/refine metric to measure watershed wide stream health | It is a biological endpoint that will reflect the improvements in stream health and function called for in the 2014 Chesapeake Watershed Agreement At this time, the index needs to be updated with the most recent macroinvertebrate data. | Management Approach (1): Identify an appropriate suite of metrics to measure the multiple facets of stream health to complement the baywide Chessie BIBI. | WP Action (1.1): Identify metrics to measure stream health | ICPRB | X
|  |  | WP Action (1.2): Establsh 2008 baseline to determine trends | ICPRB, USGS, SHWG | X
Scientific and Technical Understanding: Credit-oriented protocols including BMP and TMDL | Robust stream restoration monitoring to evaluate the potential functional lift or improvement in stream functions from BMP implementation | Management Approach (1): Identify an appropriate suite of metrics to measure the multiple facets of stream health to complement the baywide Chessie BIBI. | WP Action (1.4): Provide BMP verification metrics when requested | SHWG, MD DNR, Habitat GIT
| Uniform design process for stream restoration that can measure change in stream functions and/project success based on a project goals and objectives. Specific to the Bay TMDL, a design process for restoration projects to reduce nutrient and sediments loads delivered downstream while at the same time ensuring optimal habitat conditions restored. |  | WP Action (4.1): Implement STAC recommendations to align stream restoation BMP protocols to optimize improvements in stream health and function | SHWG, USWG, USACE, STAC, USGS
| Targeting procedures for costeffective restoration actions and design approaches that will achieve both water quality and biological functional improvement |  | WP Action (4.2): Address 4c non-pollution impairments by providing recommendations to the TMDL process | SHWG, VA DEQ, WV DEP, PA DEP, NY DEP, FWS, MDE, USGS
Scientific and Techical Understanding: Scientific knowledge of stream restoration and management | Sufficiency of data to demonstrate effectiveness of stream restoration practices | Management Approach (3): Active and engaged participation by local communities with Federal and State partners is central to Bay restoration (see Management Strategy for full Approach). | WP Action (3.3): Establish minimum stability monitoring reqiurements | South River Federation, FWS, MDE, Severn River Keeper, VA DEQ, USGS
Habitat Condition: Physical, chemical, and biological factors that impair or limit stream health recovery (watershed-based factors) |  | Management Approach: Promote watershed restoration understanding that the stream corridor includes and is affected by watershed functions
Habitat Condition: In-stream channel or floodplain stressors that impair or limit stream health recovery including but not limited to: excess nutrients and sediments, toxic contaminents, channel and bank instability, impervious surfaces, and loss of riparian forest areas. |  | Management Approach: Restore streams with the understanding that the health and function of streams affects the local stream environment as well as the downstream waters to the Bay.
Use Conflict: Limited funding for local restoration | Adequate financial resources to support local implementation efforts | Management Approach: Support efforts to increase funding for implementation of local projects and incorporate stream restoration whenever appropriate
Use Conflict: Land availbility in urban areas to install BMPs | Availability of land to retrofit and implement upland BMPs | Management Approach: Ensure that BMPs are considered for available land during development