## Required Table
SAV Outcome | Sustain and increase the habitat benefits of SAV (underwater grasses) in the Chesapeake Bay. Achieve and sustain the ultimate outcome of 185,000 acres of SAV Bay-wide necessary for a restored Bay. Progress toward this ultimate outcome will be measured against a target of 90,000 acres by 2017 and 130,000 acres by 2025.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | How to you track whether action is complete? | Expected Response | Lessons learned | Adaptations made or recommended | Critical Action
Public Engagement: Communication strategy | Lack of communication strategy | Management Approach 4: Enhance Research, Citizen Involvement, and Education in the Chesapeake Bay watershed | 13. Develop a communication strategy that enhances the public's knowledge of and appreciation for SAV in the Chesapeake Bay, similar to the models used to advance oyster and other wildlife restoration efforts. | SAV Workgroup | Final report, product | Public perception of SAV improves | not complete, necessary | recommend that we do this, SAV PR necessary to adequately protect it | x
Legislative Engagement: Protection of existing SAV | Lack of compiled statutes and regulations | Management Approach 2: Protect existing Submerged Aquatic Vegetation in the Chesapeake Bay | 3.Evaluate and enhance current statutes and regulations that protect existing SAV in the Chesapeake Bay. | SAV Workgroup | Final report, product | Regulations protecting SAV are enhances, SAV is better protected | not complete, necessary | recommend that we do this, enhance SAV regs necessary to adequately protect it | x
Partner Coordination: SAV plantings | Funding for larger scale plantings | Management Approach 3: Restore Submerged Aquatic Vegetation in the Chesapeake Bay | 7. Plant, at minumum, 20 acres of SAV seeds and propagules in appropriate high water quality/clarity areas each year until goal is reached. | MD DNR, VIMS | Acres planted | SAV recovery in areas planted | this effort is minimally beneficial to actual SAV recovery but worthwile as a tool for publich outreach | recommend that this be used as a tool for outreach and public engagement rather than soley for restoration | x
Partner Coordination: Including SAV in other projects | Funding for SAV-specific projects | Management Approach 3: Restore Submerged Aquatic Vegetation in the Chesapeake Bay | 8. Look for opportunities to optimize conditions that would allow for the natural or assisted restoration of SAV when possible and appropriate in the course of completing other non-SAV specific projects. | USACE - Baltimore
Use Conflict: Including SAV in other projects
Scientific and Technical Understanding: SAV component of shallow water model | Various research needs | Management Approach 1: Restore Water Clarity in the Chesapeake Bay | 2. Continue to improve the SAV component of shallow water model | ODU | Final report, product | SAV restoration priority areas more clearly defined | this is not a simple task…
Scientific and Technical Understanding: SAV ecosystem services | Lack of understanding of SAV ecosystem services | Management Approach 2: Protect existing Submerged Aquatic Vegetation in the Chesapeake Bay | 6. Work towards determining the economic value of SAV ecosystem services. Knowing the economic value of a resource is vital to its long-term protection. | UMCES, GMU, MD DNR | Final report, product | SAV better protected | SAV value per acre is variable depending on factors included in assessment
Scientific and Technical Understanding: SAV science | Lack of enhanced knowledge to inform restoration activities and predict SAV trends in the Bay | Management Approach 4: Enhance Research, Citizen Involvement, and Education in the Chesapeake Bay watershed | 9. Advance knowledge in the fields of SAV Biology, Ecology, and Genetics. | UMCES, AACC, USGS VIMS, UMD, UVA | Final report, product | variable, depending on research topic | see TS III | change this strategy action to "track knowledge" rather than advance knowledge as CBP is not ultimately responsibel for the research | x
Scientific and Technical Understanding: Restoration techniques | Lack of enhanced knowledge to inform restoration activities | Management Approach 4: Enhance Research, Citizen Involvement, and Education in the Chesapeake Bay watershed | 11. Advance knowledge of SAV restoration techniques. | AACC, UMCES, UMD, VIMS, MD DNR | Final report, product | restoration success improves | seeding is more feasible than transplant. Restoring for diversity is as important as restoring for acreage. Genetics are important as well. | change this strategy action to "track knowledge" rather than advance knowledge as CBP is not ultimately responsibel for the research | x
Scientific and Technical Understanding: Technical Synthesis III | Funding and staff time | Management Approach 4: Enhance Research, Citizen Involvement, and Education in the Chesapeake Bay watershed | 12. Complete and publish the third Technical Synthesis of research regarding SAV in the Chesapeake Bay. This document will highlight everything that is known, to date, regarding SAV in the Chesapeake Bay. | SAV Workgroup | Final report, product | management implications published, SAV better protected | multiple lessons and management implications from TS III | recommend that this get completed soon…..
Scientific and Technical Understanding: Climate change effects | Lack of knowledge of SAV stressors | Management Approach 4: Enhance Research, Citizen Involvement, and Education in the Chesapeake Bay watershed | 10. Advance knowledge regarding the effects of human induced stressors on SAV, including those of Climate Change. | SERC, UMCES, USGS, UMD MD DNR, VIMS, SAV Workgroup, CBP Climate Change Coordinator, Sustainable Fisheries GIT | Final report, product | avoid exaccerbation of human-induced stressors | we need to manage what we can to counter balance climate change impacts that we can't manage for. Improving water clarity will be key. | change this strategy action to "track knowledge" rather than advance knowledge as CBP is not ultimately responsibel for the research | x
Climate Change: Effects on future SAV
Habitat Condition: Water clarity | Poor water clarity conditions in the Bay | Management Approach 1: Restore Water Clarity in the Chesapeake Bay | 1.Continue work to achieve water clarity/SAV standards in areas designated for SAV use - see Water Quality GIT Workplan | Bay States, Water Quality GIT | Final report, product | SAV recovery baywide | water clarity will facilitate recovery of SAV, SAV will facilitate improvement of water clarity. Multiple factors affect water clarity. | change this strategy action to "support efforts to achieve" rather than "work to achieve" as SAV Workgroup and HGIT are not ultimately responsibel for water clarity… | x
Habitat Condition: Monitor existing SAV | Funding | Management Approach 2: Protect existing Submerged Aquatic Vegetation in the Chesapeake Bay | 4. Monitor SAV throughout Chesapeake Bay | VIMS, EPA, MD DNR, USFWS, Ba Co DEPS, DoD | Final report, acres mapped | gauge restoration success for both SAV wand water quality | this is essential to gauge restoration success. Need to incorporate citizen scientists in effort. Need stable funding. | as this pertains to the VIMS SAV monitoring program, recommend changing to "support SAV monitoring program" . Would like to add to this action the creation of sentinel sites around the bay where the SAV workgroup and members would conduct annual surveys. | x
Biota: Invasive species | Funding and staff time | Management Approach 2: Protect existing Submerged Aquatic Vegetation in the Chesapeake Bay | 5. Manage invasive species (both plant and animal) that are considered detrimental to existing SAV populations (ie. Trapa natans, Mute swan). | MD DNR, USFWS, NPS, USGS, VA DGIF | Report of annual effort, bushels of Trapa removed, number of swans eradicated or eggs oiled. | SAV recovery in areas where invasive removed | this is minimally important to SAV recovery at this point | this should be removed from the workplan, or changed to "track management of invasive species…"

## Full Table
Outcome Name | Outcome language as stated in the Chesapeake Bay Watershed Agreement.
Factor | Gap | Management Approach | Work Plan Action | Resp Party | How do you track whether action is complete? | Expected Response | Lesson(s) Learned | Adaptation(s) Made or Recommended | Critical Action
e.g.: Use Conflict: Limited financial resources | e.g.: Fish Passage Workgroup will need more than $20 million in project implementation funds in order to meet Outcome | e.g.: Prioritize dam removal projects to ensure the strategic investment of public funds | e.g.: Identify high-priority watersheds in MD, PA and VA in which to focus fish passage efforts | e.g.: Fish Passage Workgroup | e.g.: High-priority watersheds identified |  |  |  | e.g.: X