## Sheet1
Brook Trout Outcome | Restore and sustain naturally reproducing Brook Trout populations in Chesapeake Bay headwater streams, with an eight percent increase in occupied habitat by 2025.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | Critical Action
Scientific and Technical Understanding: Climate Change | Lack of future stream temperature/groundwater influence data with which to inform conservation decisions | Management Approach 1: Identify and Communicate Priority Focal Areas for Brook Trout Conservation | WP Action 1.1: Target and conserve wild brook trout populations in sub-watersheds that have best potential for sustaining resiliency | EBTJV, MD DNR, VA DGIF, WV DNR, PA FBC | X
| Need for better coordination of climate change data in decision support tools | Management Approach 3: Refine and Apply Decision Support Tools | WP Action 3.1: Apply decision support tools to target stream restoration projects for brook trout, including habitats vulnerable to fragmentation and groundwater influences | USDA Forest Service, Climate Change WG, USGS, Stream Health WG | X
Scientific and Technical Understanding: Habitat Stressors | Need for better coordination of AMD/UOG data for decision support tools | Management Approach 2: Consider Climate Change and Emerging Stressors in Determining Restoration Priorities | WP Action 2.1: Add predictive layer for acid mine drainage-impacted streams and unconventional oil and gas development | USGS, WVU, Habitat GIT
| Need for more expansive invasive/exotic species research and monitoring | Management Approach 2: Consider Climate Change and Emerging Stressors in Determining Restoration Priorities | WP Action 2.2: Consider impact of invasive species on brook trout habitat to better influence management of habitats and surrounding watersheds | USGS, MAPAIS, Habitat GIT | X
| Need for better coordination of habitat stressor data in decision support tools | Management Approach 3: Refine and Apply Decision Support Tools | WP Action 3.1: Apply decision support tools to target stream restoration projects for brook trout, including habitats vulnerable to fragmentation and groundwater influences | USDA Forest Service, Climate Change WG, USGS, Stream Health WG | X
Scientific and Technical Understanding: Monitoring | Lack of method with which to correlate habitat restoration to improvements in brook trout population health; Need for development of yearly occupancy reporting process | Management Approach 4: Continue and Expand Brook Trout monitoring efforts | WP Action 4.1: Continue assistance to states in monitoring brook trout occupancy and develop indicator using this data | MD, VA, PA, NY, WV | X
| No specifically identified gap(s) correspond(s) to this Factor | Management Approach 4: Continue and Expand Brook Trout monitoring efforts | WP Action 4.2: Collect genetic information as potential census method for determining population viability and long-term restoration success | UMASS Amherst
Scientific and Technical Understanding: Refinement and coordination of use of decision support tools | Lack of future stream temperature data with which to inform conservation decisions | Management Approach 1: Identify and Communicate Priority Focal Areas for Brook Trout Conservation | WP Action 1.1: Target and conserve wild brook trout populations in sub-watersheds that have best potential for sustaining resiliency | EBTJV, MD DNR, VA DGIF, WV DNR, PA FBC | X
| Need for better coordination of AMD/UOG data for decision support tools | Management Approach 2: Consider Climate Change and Emerging Stressors in Determining Restoration Priorities | WP Action 2.1: Add predictive layer for acid mine drainage-impacted streams and unconventional oil and gas development | USGS, WVU, Habitat GIT
| Need for better coordination, reporting of data with which to populate decision support tools | Management Approach 3: Refine and Apply Decision Support Tools | WP Action 3.1: Apply decision support tools to target stream restoration projects for brook trout, including habitats vulnerable to fragmentation and groundwater influences | USDA Forest Service, Climate Change WG, USGS, Stream Health WG | X
Scientific and Technical Understanding: Restoration | No specifically identified gap(s) correspond(s) to this Factor | Management Approach 2: Consider Climate Change and Emerging Stressors in Determining Restoration Priorities | WP Action 2.3: Implement Trout Unlimited's Home River Initiatives (Potomac Headwaters, Shenandoah, and Upper James River), which focus riparian and in-stream restoration efforts on cold water streams. | Trout Unlimited | X
| Need for decision support tool coordination and training for practitioners in order to best guide restoration efforts | Management Approach 3: Refine and Apply Decision Support Tools | WP Action 3.1: Apply decision support tools to target stream restoration projects for brook trout, including habitats vulnerable to fragmentation and groundwater influences | USDA Forest Service, Climate Change WG, USGS, Stream Health WG | X
Government Agency Engagement: Monitoring | No specifically identified gap(s) correspond(s) to this Factor | Management Approach 4: Continue and Expand Brook Trout monitoring efforts | WP Action 4.1: Continue assistance to states in monitoring brook trout occupancy and develop indicator using this data | MD, VA, PA, NY, WV | X
Government Agency Engagement: Decision-maker and public awareness of brook trout issues | Lack of method of communication with which to educate and engage decision makers on priority brook trout habitat for conservation | Management Approach 1: Identify and Communicate Priority Focal Areas for Brook Trout Conservation | WP Action 1.2: Communicate "best of the best" patches in context of local conservation planning | CBP GIS Team, LGAC, Healthy Watersheds GIT, Upper Gunpowder Watershed Conservancy | X
Government Agency Engagement: Habitat Protection | Lack of method of communication with which to educate and engage decision makers on priority brook trout habitat for conservation | Management Approach 1: Identify and Communicate Priority Focal Areas for Brook Trout Conservation | WP Action 1.1: Target and conserve wild brook trout populations in sub-watersheds that have best potential for sustaining resiliency | EBTJV, MD DNR, VA DGIF, WV DNR, PA FBC | X
| Lack of method of communication with which to educate and engage decision makers on priority brook trout habitat for conservation | Management Approach 1: Identify and Communicate Priority Focal Areas for Brook Trout Conservation | WP Action 1.2: Communicate "best of the best" patches in context of local conservation planning | CBP GIS Team, LGAC, Healthy Watersheds GIT, Upper Gunpowder Watershed Conservancy | X
| Lack of government agency awareness of/engagement with decision support tools with which to direct habitat conservation activities | Management Approach 3: Refine and Apply Decision Support Tools | WP Action 3.1: Apply decision support tools to target stream restoration projects for brook trout, including habitats vulnerable to fragmentation and groundwater influences | USDA Forest Service, Climate Change WG, USGS, Stream Health WG | X
NGO Engagement: Coordination with restoration groups to target opportunities to increase habitat and presence | Need for more NGO engagement in brook trout restoration efforts | Management Approach 2: Consider Climate Change and Emerging Stressors in Determining Restoration Priorities | WP Action 2.3: Implement Trout Unlimited's Home River Initiatives (Potomac Headwaters, Shenandoah, and Upper James River), which focus riparian and in-stream restoration efforts on cold water streams. | Trout Unlimited | X
Partner Coordination: Refinement and coordination of use of decision support tools | No specifically identified gap(s) correspond(s) to this Factor | Management Approach 1: Identify and Communicate Priority Focal Areas for Brook Trout Conservation | WP Action 1.2: Communicate "best of the best" patches in context of local conservation planning | CBP GIS Team, LGAC, Healthy Watersheds GIT, Upper Gunpowder Watershed Conservancy | X
| Lack of coordination in reporting AMD/UOG data | Management Approach 2: Consider Climate Change and Emerging Stressors in Determining Restoration Priorities | WP Action 2.1: Add predictive layer for acid mine drainage-impacted streams and unconventional oil and gas development | USGS, WVU, Habitat GIT
| Need for decision support tool coordination and training for practitioners in order to best guide habitat protection and restoration efforts | Management Approach 3: Refine and Apply Decision Support Tools | WP Action 3.1: Apply decision support tools to target stream restoration projects for brook trout, including habitats vulnerable to fragmentation and groundwater influences | USDA Forest Service, Climate Change WG, USGS, Stream Health WG | X
| No specifically identified gap(s) correspond(s) to this Factor | Management Approach 3: Refine and Apply Decision Support Tools | WP Action 3.2: Host dialogue on varied brook trout angling regulations across states and in National Parks | MD, VA, PA, NY, WV, and Shenandoah NP
Partner Coordination: Monitoring | No specifically identified gap(s) correspond(s) to this Factor | Management Approach 4: Continue and Expand Brook Trout monitoring efforts | WP Action 4.1: Continue assistance to states in monitoring brook trout occupancy and develop indicator using this data | MD, VA, PA, NY, WV | X
| No specifically identified gap(s) correspond(s) to this Factor | Management Approach 4: Continue and Expand Brook Trout monitoring efforts | WP Action 4.2: Collect genetic information as potential census method for determining population viability and long-term restoration success | UMASS Amherst
Factors Influencing
Legislative Agency Engagement: Decision-maker and public awareness of brook trout issues | Lack of method of communication with which to educate and engage decision makers on priority brook trout habitat for conservation; No current path with which to include BT priorities in WIPs | No identified Management Approach and/or Work Plan Action
Public Engagement: Restoration | Lack of creative or innovative ways to incentivize private landowner participation | No identified Management Approach and/or Work Plan Action
Public Engagement: Habitat Protection | Lack of creative or innovative ways to incentivize private landowner participation | No identified Management Approach and/or Work Plan Action
NGO Engagement: Decision-maker and public awareness of brook trout issues | Seek partnerships with land trusts/NGOs in order to influence public engagement | No identified Management Approach and/or Work Plan Action
Partner Coordination: Funding | Need for coordination amongst partners to locate and actively apply for grants to cover monitoring/restoration efforts | No identified Management Approach and/or Work Plan Action
Science and Technical Understanding: Monitoring | Need to consider invasive/exotic species monitoring; need for climate change, forest buffer, stream health, protected lands metric with which to monitor/inform outcome progress (possibly tie to other outcome indicator) | No identified Management Approach and/or Work Plan Action
Legislative Agency Engagement: Funding |  | No identified Management Approach and/or Work Plan Action
Government Agency Engagement: Funding |  | No identified Management Approach and/or Work Plan Action