## Final Table
Fish Habitat Outcome | Continually improve the effectiveness of fish habitat conservation and restoration efforts by identifying and characterizing critical fish and shellfish spawning, nursery and forage areas within the Chesapeake Bay and its tributaries. Use existing and new tools to integrate information and conduct assessments to inform restoration and conservation efforts.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | Critical Action
e.g.: Use Conflict: Limited financial resources | e.g.: Fish Passage Workgroup will need more than $20 million in project implementation funds in order to meet Outcome | e.g.: Prioritize dam removal projects to ensure the strategic investment of public funds | e.g.: Identify high-priority watersheds in MD, PA and VA in which to focus fish passage efforts | e.g.: Fish Passage Workgroup | e.g.: X
Scientific and Technical Understanding: Management prioritization, funding and commitment | Jurisdictions have limited regulatory authority to strengthen habitat protections. Funding for new research is limited and requires additional coordination and management to improve efficiency. | Management Approach (1): Identify and prioritize existing and emerging threats to fish habitat and propose actions to manage them | WP Action (1.1): Continue to improve our understanding of specific habitat stressors including temporal considerations to promote sound management strategies to conserve and restore habitat for productive fisheries | Fish Habitat Action Team | X
|  |  | WP Action (1.2): Work with Chesapeake Bay Program partners and Goal Implementation Teams to identify threats and understand how those threats are being addressed. | Fish Habitat Action Team | X
|  |  | WP Action (1.3) : Develop thresholds and/or metrics for primary stressors and threats in order to characterize the aspects of habitat that need to be maintained to support fish habitat functions | Fish Habitat Action Team
Scientific and Technical Understanding: impacts of fish habitat on fisheries production | Scientific gaps include a limited understanding of the contributions fish habitats make to fisheries production and the impact environmental factors can have on spawning, larval development, and recruitment of adults. | Management Approach (1): Identify and prioritize existing and emerging threats to fish habitat and propose actions to manage them | WP Action (1.1): Continue to improve our understanding of specific habitat stressors including temporal considerations to promote sound management strategies to conserve and restore habitat for productive fisheries | Fish Habitat Action Team | X
|  |  | WP Action (1.2): Work with Chesapeake Bay Program partners and Goal Implementation Teams to identify threats and understand how those threats are being addressed. | Fish Habitat Action Team | X
|  |  | WP Action (1.3) : Develop thresholds and/or metrics for primary stressors and threats in order to characterize the aspects of habitat that need to be maintained to support fish habitat functions | Fish Habitat Action Team
Scientific and Technical Understanding: Lack of information and understanding on species in their habitats and identifying habitat areas. | Improved information on fish distributions and habitats could support the understanding and evaluation of habitat connections and fish distribution drivers. | Management Approach (2): Compile and identify data on habitats, habitat vulnerabilities, and fish utilization at different life stages to develop a set of criteria for identifying areas of high-value fish habitat | WP Action (2.1): Incorporate fish habitat utilization information into a threat matrix | Fish Habitat Action Team, Delaware Department of Natural Resources and Environmental Control
|  |  | WP Action (2.2): Complete fish population and abundance surveys at select U.S. Department of Defense installations and provide relevant data for species of interest | Department of Defense
Scientific and Technical Understanding: need to integrate and synthesize existing data into decision support tools | Existing data needs to be compiled and made accessible to managers to improve decision-making process. | Management Approach (2): Compile and identify data on habitats, habitat vulnerabilities, and fish utilization at different life stages to develop a set of criteria for identifying areas of high-value fish habitat | WP Action (2.1): Incorporate fish habitat utilization information into a threat matrix | Fish Habitat Action Team, Delaware Department of Natural Resources and Environmental Control
|  |  | WP Action (2.2): Complete fish population and abundance surveys at select U.S. Department of Defense installations and provide relevant data for species of interest | Department of Defense
Scientific and Technical Understanding: GIS Capacity | Geographic information related to fish habitat and utilization at different life stages could allow us to quantify and target high-quality habitat for management action. Scientific gaps include a limited understanding of where and how many areas of "high quality" fish habitat are located within the watershed, which could suggest which waters are most important to critical life stages for fish. Further, many wildlife action plans and spatial tools do not characterize the "quality" of the fish habitat they identify. | Management Approach (3): Map and target high-value fish habitat for informed management decisions and improved conservation and restoration | WP Action (3.1): Overlay spatial data on the seasonal ranges of priority fish species with high-value habitats | Fish Habitat Action Team, Maryland Department of Natural Resources, NOAA Chesapeake Bay Office | X
|  |  | WP Action (3.2): Identify and, where possible, fill spatial data gaps for specific fish species and/or tributaries that lack sufficient data coverage | Fish Habitat Action Team | X
Scientific and Technical Understanding: Availability and applicability of integrative tools | Geographic information related to fish habitat and utilization at different life stages could allow us to quantify and target high-quality habitat for management action. Scientific gaps include a limited understanding of where and how many areas of "high quality" fish habitat are located within the watershed, which could suggest which waters are most important to critical life stages for fish. Further, many wildlife action plans and spatial tools do not characterize the "quality" of the fish habitat they identify. | Management Approach (3): Map and target high-value fish habitat for informed management decisions and improved conservation and restoration | WP Action (3.1): Overlay spatial data on the seasonal ranges of priority fish species with high-value habitats | Fish Habitat Action Team, Maryland Department of Natural Resources, NOAA Chesapeake Bay Office | X
|  |  | WP Action (3.2): Identify and, where possible, fill spatial data gaps for specific fish species and/or tributaries that lack sufficient data coverage | Fish Habitat Action Team | X
Scientific and Technical Understanding: funding | Funding for new research is limited and is necessary to advance targeting of high-value fish habitat | Management Approach (3): Map and target high-value fish habitat for informed management decisions and improved conservation and restoration | WP Action (3.1): Overlay spatial data on the seasonal ranges of priority fish species with high-value habitats | Fish Habitat Action Team, Maryland Department of Natural Resources, NOAA Chesapeake Bay Office | X
|  |  | WP Action (3.2): Identify and, where possible, fill spatial data gaps for specific fish species and/or tributaries that lack sufficient data coverage | Fish Habitat Action Team | X
Scientific and Technical Understanding: Funding and coordination | Information on the economic contribution of fish habitat | Management Approach (5): Evaluate ways to enhance fish habitat protection by reviewing examples from other regions and actively engaging with the Atlantic Coast Fish Habitat Partnership | WP Action (5.1): Engage and communicate fish habitat value (including ecosystem services) to local planners and restoration practitioners | LGAC | X
|  |  | WP Action (5.2): Work with partners who are implementing fish habitat conservation projects | Fish Habitat Action Team | X
|  |  | WP Action (5.3): Complete a review and analysis of fish habitat conservation efforts taking place in other regions around the country | Fish Habitat Action Team
|  |  | WP Action (5.4): Explore avenues to develop a review of cultural views and policies that may limit the promotion of habitat conservation | Fish Habitat Action Team
Government Agency Engagement at the Federal, State and/or Local Levels: Public and local government understanding, multiagency coordination and the permitting process. | Public knowledge can be improved to expand understanding of fish habitat loss on valued community and recreational services. Local communities should be more involved in fish habitat protection (especially when it comes to including fish habitat protections in local planning efforts). Improved communication on the threats driving habitat loss and what habitat loss means to people are needed. Need a communication process/strategy for local levels. | Management Approach (4): Communicate the importance of fish habitat and the tradeoffs associated with competing uses of land and water to the general public and local community leaders | WP Action (4.1): Engage and communicate fish habitat needs to partners and local communities | Fish Habitat Action Team; LGAT | X
Government Agency Engagement at the Federal, State and/or Local Levels: community opposition to land use regulations | Information on the economic contribution of fish habitat, need storyboards and opportunities to communicate with decision makers | Management Approach (5): Evaluate ways to enhance fish habitat protection by reviewing examples from other regions and actively engaging with the Atlantic Coast Fish Habitat Partnership | WP Action (5.1): Engage and communicate fish habitat value (including ecosystem services) to local planners and restoration practitioners | LGAC | X
|  |  | WP Action (5.2): Work with partners who are implementing fish habitat conservation projects | Fish Habitat Action Team | X
Partner Coordination: Improve coverage of the Chesapeake Bay | Multiagency coordination could be improved and cover different spatial scales (from watershed-wide to the local level). | Management Approach (3): Map and target high-value fish habitat for informed management decisions and improved conservation and restoration | WP Action (3.1): Overlay spatial data on the seasonal ranges of priority fish species with high-value habitats | Fish Habitat Action Team, Maryland Department of Natural Resources, NOAA Chesapeake Bay Office | X
|  |  | WP Action (3.2): Identify and, where possible, fill spatial data gaps for specific fish species and/or tributaries that lack sufficient data coverage | Fish Habitat Action Team | X
Partner Coordination : lack of public understanding of habitat loss | Engagement with organizations outside the Chesapeake Bay is needed to incorporate research findings, new spatial and data tools and analysis, as well as preventing the unnecessary duplication of efforts. | Management Approach (5): Evaluate ways to enhance fish habitat protection by reviewing examples from other regions and actively engaging with the Atlantic Coast Fish Habitat Partnership | WP Action (5.2): Work with partners who are implementing fish habitat conservation projects | Fish Habitat Action Team | X
|  |  | WP Action (5.4): Explore avenues to develop a review of cultural views and policies that may limit the promotion of habitat conservation | Fish Habitat Action Team
Public Engagement: Management prioritization, funding and commitment | Public knowledge can be improved to expand understanding of fish habitat loss on valued community and recreational services. Improved communication on the threats driving habitat loss and what habitat loss means to people are needed. Dedicated funding and effort to engage the public, develop trust and open communication could increase support and understanding of fish habitat function, ecosystem benefits, and public benefits | Management Approach (4): Communicate the importance of fish habitat and the tradeoffs associated with competing uses of land and water to the general public and local community leaders | WP Action (4.1): Engage and communicate fish habitat needs to partners and local communities | Fish Habitat Action Team | X
Factors Influencing Success from Management Strategy
Use Conflict: Fishing activities (including dredging) | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Use Conflict: Gas and mineral extraction and acid mine drainage | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Population Growth: Development and land use change (including the hardening of shorelines, increased impervious surface) | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Water quality | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Habitat loss (including the loss of bottom habitat, underwater grasses, habitat structure, wetlands, and forest cover) | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Predatory invasive species | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Watershed fragmentation | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Barriers to fish migration | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Temperature rise | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Sea level rise | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Saltwater intrusion | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Changes in freshwater flow | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Ocean acidification | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified

## Full Table
Fish Habitat Outcome | Continually improve the effectiveness of fish habitat conservation and restoration efforts by identifying and characterizing critical fish and shellfish spawning, nursery and forage areas within the Chesapeake Bay and its tributaries. Use existing and new tools to integrate information and conduct assessments to inform restoration and conservation efforts.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | How do you track whether action is complete? | Expected Response | Lesson(s) Learned | Adaptation(s) Made or Recommended | Critical Action (Indicate with an X)
e.g.: Use Conflict: Limited financial resources | e.g.: Fish Passage Workgroup will need more than $20 million in project implementation funds in order to meet Outcome | e.g.: Prioritize dam removal projects to ensure the strategic investment of public funds | e.g.: Identify high-priority watersheds in MD, PA and VA in which to focus fish passage efforts | e.g.: Fish Passage Workgroup | e.g.: High-priority watersheds identified |  |  |  | e.g.: X
Scientific and Technical Understanding: Management prioritization, funding and commitment | Jurisdictions have limited regulatory authority to strengthen habitat protections. Funding for new research is limited and requires additional coordination and management to improve efficiency. | Management Approach (1): Identify and prioritize existing and emerging threats to fish habitat and propose actions to manage them | WP Action (1.1): Continue to improve our understanding of specific habitat stressors including temporal considerations to promote sound management strategies to conserve and restore habitat for productive fisheries | Fish Habitat Action Team | Continue supporting and sharing research with partners | Use data and information to support future efforts | Need to have a communications strategy to ensure data is used |  | X
|  |  | WP Action (1.2): Work with Chesapeake Bay Program partners and Goal Implementation Teams to identify threats and understand how those threats are being addressed. | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
|  |  | WP Action (1.3) : Develop thresholds and/or metrics for primary stressors and threats in order to characterize the aspects of habitat that need to be maintained to support fish habitat functions | Fish Habitat Action Team | N/A | N/A | N/A | N/A
Scientific and Technical Understanding: impacts of fish habitat on fisheries production | Scientific gaps include a limited understanding of the contributions fish habitats make to fisheries production and the impact environmental factors can have on spawning, larval development, and recruitment of adults. | Management Approach (1): Identify and prioritize existing and emerging threats to fish habitat and propose actions to manage them | WP Action (1.1): Continue to improve our understanding of specific habitat stressors including temporal considerations to promote sound management strategies to conserve and restore habitat for productive fisheries | Fish Habitat Action Team | Continue supporting and sharing research with partners | Use data and information to support future efforts | Need to have a communications strategy to ensure data is used |  | X
|  |  | WP Action (1.2): Work with Chesapeake Bay Program partners and Goal Implementation Teams to identify threats and understand how those threats are being addressed. | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
|  |  | WP Action (1.3) : Develop thresholds and/or metrics for primary stressors and threats in order to characterize the aspects of habitat that need to be maintained to support fish habitat functions | Fish Habitat Action Team | N/A | N/A | N/A | N/A
Scientific and Technical Understanding: Lack of information and understanding on species in their habitats and identifying habitat areas. | Improved information on fish distributions and habitats could support the understanding and evaluation of habitat connections and fish distribution drivers. | Management Approach (2): Compile and identify data on habitats, habitat vulnerabilities, and fish utilization at different life stages to develop a set of criteria for identifying areas of high-value fish habitat | WP Action (2.1): Incorporate fish habitat utilization information into a threat matrix | Fish Habitat Action Team, Delaware Department of Natural Resources and Environmental Control | Fish Habitat threat and stressor matrix assembled | Use matrices for communications efforts | Need to have a communications strategy to ensure data is used
|  |  | WP Action (2.2): Complete fish population and abundance surveys at select U.S. Department of Defense installations and provide relevant data for species of interest | Department of Defense | Department of Defense produced final Integrated Natural Resources Management Plan, Naval Weapons Station Yorktown (2010-2020) | N/A | N/A
Scientific and Technical Understanding: need to integrate and synthesize existing data into decision support tools | Existing data needs to be compiled and made accessible to managers to improve decision-making process. | Management Approach (2): Compile and identify data on habitats, habitat vulnerabilities, and fish utilization at different life stages to develop a set of criteria for identifying areas of high-value fish habitat | WP Action (2.1): Incorporate fish habitat utilization information into a threat matrix | Fish Habitat Action Team, Delaware Department of Natural Resources and Environmental Control | Fish Habitat threat and stressor matrix assembled | Use matrices for communications efforts | Need to have a communications strategy to ensure data is used
|  |  | WP Action (2.2): Complete fish population and abundance surveys at select U.S. Department of Defense installations and provide relevant data for species of interest | Department of Defense | Department of Defense produced final Integrated Natural Resources Management Plan, Naval Weapons Station Yorktown (2010-2020) | N/A | N/A
Scientific and Technical Understanding: GIS Capacity | Geographic information related to fish habitat and utilization at different life stages could allow us to quantify and target high-quality habitat for management action. Scientific gaps include a limited understanding of where and how many areas of "high quality" fish habitat are located within the watershed, which could suggest which waters are most important to critical life stages for fish. Further, many wildlife action plans and spatial tools do not characterize the "quality" of the fish habitat they identify. | Management Approach (3): Map and target high-value fish habitat for informed management decisions and improved conservation and restoration | WP Action (3.1): Overlay spatial data on the seasonal ranges of priority fish species with high-value habitats | Fish Habitat Action Team, Maryland Department of Natural Resources, NOAA Chesapeake Bay Office | N/A | N/A | N/A | N/A | X
|  |  | WP Action (3.2): Identify and, where possible, fill spatial data gaps for specific fish species and/or tributaries that lack sufficient data coverage | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
Scientific and Technical Understanding: Availability and applicability of integrative tools | Geographic information related to fish habitat and utilization at different life stages could allow us to quantify and target high-quality habitat for management action. Scientific gaps include a limited understanding of where and how many areas of "high quality" fish habitat are located within the watershed, which could suggest which waters are most important to critical life stages for fish. Further, many wildlife action plans and spatial tools do not characterize the "quality" of the fish habitat they identify. | Management Approach (3): Map and target high-value fish habitat for informed management decisions and improved conservation and restoration | WP Action (3.1): Overlay spatial data on the seasonal ranges of priority fish species with high-value habitats | Fish Habitat Action Team, Maryland Department of Natural Resources, NOAA Chesapeake Bay Office | N/A | N/A | N/A | N/A | X
|  |  | WP Action (3.2): Identify and, where possible, fill spatial data gaps for specific fish species and/or tributaries that lack sufficient data coverage | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
Scientific and Technical Understanding: funding | Funding for new research is limited and is necessary to advance targeting of high-value fish habitat | Management Approach (3): Map and target high-value fish habitat for informed management decisions and improved conservation and restoration | WP Action (3.1): Overlay spatial data on the seasonal ranges of priority fish species with high-value habitats | Fish Habitat Action Team, Maryland Department of Natural Resources, NOAA Chesapeake Bay Office | N/A | N/A | N/A | N/A | X
|  |  | WP Action (3.2): Identify and, where possible, fill spatial data gaps for specific fish species and/or tributaries that lack sufficient data coverage | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
Scientific and Technical Understanding: Funding and coordination | Information on the economic contribution of fish habitat | Management Approach (5): Evaluate ways to enhance fish habitat protection by reviewing examples from other regions and actively engaging with the Atlantic Coast Fish Habitat Partnership | WP Action (5.1): Engage and communicate fish habitat value (including ecosystem services) to local planners and restoration practitioners | LGAC | N/A | N/A | N/A | N/A | X
|  |  | WP Action (5.2): Work with partners who are implementing fish habitat conservation projects | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
|  |  | WP Action (5.3): Complete a review and analysis of fish habitat conservation efforts taking place in other regions around the country | Fish Habitat Action Team | N/A | N/A | N/A | N/A
|  |  | WP Action (5.4): Explore avenues to develop a review of cultural views and policies that may limit the promotion of habitat conservation | Fish Habitat Action Team | N/A | N/A | N/A | N/A
Government Agency Engagement at the Federal, State and/or Local Levels: Public and local government understanding, multiagency coordination and the permitting process. | Public knowledge can be improved to expand understanding of fish habitat loss on valued community and recreational services. Local communities should be more involved in fish habitat protection (especially when it comes to including fish habitat protections in local planning efforts). Improved communication on the threats driving habitat loss and what habitat loss means to people are needed. Need a communication process/strategy for local levels. | Management Approach (4): Communicate the importance of fish habitat and the tradeoffs associated with competing uses of land and water to the general public and local community leaders | WP Action (4.1): Engage and communicate fish habitat needs to partners and local communities | Fish Habitat Action Team; LGAT | N/A | N/A | N/A | N/A | X
Government Agency Engagement at the Federal, State and/or Local Levels: community opposition to land use regulations | Information on the economic contribution of fish habitat, need storyboards and opportunities to communicate with decision makers | Management Approach (5): Evaluate ways to enhance fish habitat protection by reviewing examples from other regions and actively engaging with the Atlantic Coast Fish Habitat Partnership | WP Action (5.1): Engage and communicate fish habitat value (including ecosystem services) to local planners and restoration practitioners | LGAC | N/A | N/A | N/A | N/A | X
|  |  | WP Action (5.2): Work with partners who are implementing fish habitat conservation projects | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
Partner Coordination: Improve coverage of the Chesapeake Bay | Multiagency coordination could be improved and cover different spatial scales (from watershed-wide to the local level). | Management Approach (3): Map and target high-value fish habitat for informed management decisions and improved conservation and restoration | WP Action (3.1): Overlay spatial data on the seasonal ranges of priority fish species with high-value habitats | Fish Habitat Action Team, Maryland Department of Natural Resources, NOAA Chesapeake Bay Office | N/A | N/A | N/A | N/A | X
|  |  | WP Action (3.2): Identify and, where possible, fill spatial data gaps for specific fish species and/or tributaries that lack sufficient data coverage | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
Partner Coordination : lack of public understanding of habitat loss | Engagement with organizations outside the Chesapeake Bay is needed to incorporate research findings, new spatial and data tools and analysis, as well as preventing the unnecessary duplication of efforts. | Management Approach (5): Evaluate ways to enhance fish habitat protection by reviewing examples from other regions and actively engaging with the Atlantic Coast Fish Habitat Partnership | WP Action (5.2): Work with partners who are implementing fish habitat conservation projects | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
|  |  | WP Action (5.4): Explore avenues to develop a review of cultural views and policies that may limit the promotion of habitat conservation | Fish Habitat Action Team | N/A | N/A | N/A | N/A
Public Engagement: Management prioritization, funding and commitment | Public knowledge can be improved to expand understanding of fish habitat loss on valued community and recreational services. Improved communication on the threats driving habitat loss and what habitat loss means to people are needed. Dedicated funding and effort to engage the public, develop trust and open communication could increase support and understanding of fish habitat function, ecosystem benefits, and public benefits | Management Approach (4): Communicate the importance of fish habitat and the tradeoffs associated with competing uses of land and water to the general public and local community leaders | WP Action (4.1): Engage and communicate fish habitat needs to partners and local communities | Fish Habitat Action Team | N/A | N/A | N/A | N/A | X
Factors Influencing Success from Management Strategy
Use Conflict: Fishing activities (including dredging) | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Use Conflict: Gas and mineral extraction and acid mine drainage | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Population Growth: Development and land use change (including the hardening of shorelines, increased impervious surface) | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Water quality | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Habitat loss (including the loss of bottom habitat, underwater grasses, habitat structure, wetlands, and forest cover) | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Predatory invasive species | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Watershed fragmentation | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Barriers to fish migration | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Temperature rise | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Sea level rise | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Saltwater intrusion | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Changes in freshwater flow | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change: Ocean acidification | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified