## Fish Passage QPM Prep
Fish Passage Outcome | Continually increase habitat to support sustainable migratory fish populations in the Chesapeake Bay watershed’s freshwater rivers and streams. By 2025, restore historical fish migration routes by opening 1,000 additional stream miles to fish passage. Restoration success will be indicated by the consistent presence of alewife, blueback herring, American shad, hickory shad, American eel and brook trout, to be monitored in accordance with available agency resources and collaboratively developed methods.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | Critical Action
Landowner Engagement: Dam owner permission to remove dams | No specifically identified gap(s) correspond(s) to this Factor | Management Approach: Target outreach to landowners in order to foster cooperation and community engagement in fish passage restoration | WP Action (1.2): Pursue dam removal incentive programs | MD | X
Landowner Engagement: Dam owner understanding of the ancillary benefits of dam removal | No specifically identified gap(s) correspond(s) to this Factor | Management Approach: Target outreach to landowners in order to foster cooperation and community engagement in fish passage restoration
State Legislative Engagement: Policy maker understanding of the ancillary benefits of dam removal | No specifically identified gap(s) correspond(s) to this Factor | Management Approach: Target outreach to state policymakers in order to foster cooperation and community engagement in fish passage restoration
State Legislative Engagement: Legislation to incentivize or mandate barrier removal projects | No specifically identified gap(s) correspond(s) to this Factor | Mangement Approach: Target outreach to state policymakers in order to foster cooperation and community engagement in fish passage restoration | WP Action (1.4): Identify legislative, budgetary and policy needs and options | Chesapeake Bay Commission
Local Legislative Engagement: Policy maker understanding of the ancillary benefits of dam removal | No specifically identified gap(s) correspond(s) to this Factor | Management Approach: Target outreach to local policymakers in order to foster cooperation and community engagement in fish passage restoration | WP Action (1.3): Establish or continue relationships with state dam safety programs to coordinate dam removal |  | X
State Government Agency Engagement: Legal action against noncompliant dams can be costly and time-consuming | No specifically identified gap(s) correspond(s) to this Factor |  |  | Fish Passage Workgroup
Use Conflict: Limited financial resources | With the average cost of stream barrier removal in Maryland, Pennsylvania, and Virginia hovering around $200,000, the Fish Passage Workgroup will need more than $20 million in project implementation funds in order to have a chance of meeting this Outcome. Further, onformation is needed to develop standardized fish passage assessment and evaluation tools (e.g., to evaluate swimming performance and energetics or to evaluate methods of motivating fish to enter and pass a diversion structure) and to develop a fish passage database to support the scientific assessment of the distribution and performance of all known upstream fish passage structures. | Management Approach (1): Continue to support dam removal projects already underway (including the removal of the Bloede and Centreville dams in Maryland; the Monumental Mills Dam in Virginia; and the Long Run and Heistand Sawmill dams in Pennsylvania) | WP Action (1.1): Continue dam removal activities in the Chesapeake Bay | Fish Passage Workgroup | X
|  | Management Approach (3): Prioritize dam removal projects to ensure strategic investment of public funds | WP Action (3.1): Continue to use the Chesapeake Bay Fish Passage Prioritization Tool to prioritize dam removal projects | Fish Passage Workgroup | X
|  |  | WP Action (3.1.1): Identify additional high-priority watersheds in Maryland, Pennsylvania and Virginia in which to focus fish passage efforts. | Fish Passage Workgroup
|  |  | WP Action (3.1.2): Conduct culvert and bridge assessments in high-priority sub-watersheds to determine extent of road- and rail-related blockages, adding new information to the Fish Passage Tool | Fish Passage Workgroup | X
|  |  | WP Action (3.1.3): Gain formal Chesapeake Bay Program acceptance of new method behind miles opened metric to support definition of upstream functional network | Fish Passage Workgroup
Habitat Condition: Populations of targeted fish species—particularly river herring, shad and American eel—have declined nationwide | No specifically identified gap(s) correspond(s) to this Factor | Management Approach (2): Document the return of fish to opened stream reaches by establishing the presence or absence of target species at a select number of fish passage projects in the Chesapeake Bay watershed | WP Action (2.1): Conduct Tier I monitoring on NOAA-funded dam removal projects for the presence or absence of target fish species | Fish Passage Workgroup
|  |  | WP Action (2.2): Conduct Tier II monitoring on select dam removals | Fish Passage Workgroup
|  |  | WP Action (2.3): Conduct boat electrofishing (target species monitoring) of Embrey and Harvell dam removals on the Rappahannock and Appomattox rivers, respectively | VA
|  |  | WP Action (2.6): Develop and test environmental DNA tools to detect river herring presence in frozen and freshly collected water samples | VA
|  |  | WP Action (2.4): Conduct annual American shad count at Bosher's vertical slot fishway | VA
|  |  | WP Action (2.5): Conduct annual backpack electrofishing (target species counts) at Claiborne Run nature-like fishway and White Oak Run pool and weir fishway | VA
|  |  | WP Action (2.6): Determine the origin (hatchery versus wild) of juvenile American shad in the James River | VA