## Wetlands Outcome Workplan
Outcome: Wetlands
Goal: Restore 15,762 acres; Enhance 30,000 acres over the next two years
Outcome: By 2025, Restore 85,000 acres; Enhance 150,000 acres
Long term Target: X by 2025
2 year Target: Y by 2018
Management Approach 1: Improve wetland mapping, and the wetland restoration reporting and tracking process.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
1. Collaborate with Wetland Expert Panel and Modeling Team to improve wetland mapping for Chesapeake Bay Watershed | Identify a methodology | Wetland Workgroup | Mainly PA and VA | ASAP | TBD
| Secure funding | Wetland Expert Panel
| Complete mapping updates | Modeling Team
2. Streamline NEIEN data collection for each State. |  | Wetland Workgroup, NEIEN Contacts for each State | All States in Watershed | Completed for NY, PA, MD, DE, and WV | 0
VA to be completed by December 2015
3. Confirm the accuracy of information reported. |  | NEIEN Contacts for each State | all States in Watershed |  |  |  | Are states willing to develop a QA/QC plan?
4. Improve mapping of tidal wetlands to document loss due to sea level rise and other factors | Identify a methodology | Wetland Workgroup | Tidal waters of MD and VA | 2016 - 2017 | TBD | Funded by USGS
| Complete mapping and compare to previous data for status and trends analysis | USGS, Climate Change Workgroup
5. Research the effects of sea-level rise, salinification, and watershed sediment loading on the resilience and services of tidal freshwater wetlands | To be developed | USGS initiative |  | 2016 - 2017 | TBD |  | funded by USGS
6. Forecast land development throughout the watershed to help assess potential wetland loss | To be developed | USGS initiative |  | 2016 - 2017 | TBD |  | funded by USGS
7. Document long-term changes in wetland acreage due to climate variability | To be developed | USGS initiative |  | 2016 - 2017 | TBD |  | funded by USGS
Total
Management Approach 2: Identify barriers to wetland restoration and develop solutions to address them.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
8. Identify barriers to wetland restoration for practitioners. | Completed | The Nature Conservancy | Pennsylvania | Completed June 2015 | Covered by NFWF grant
|  | Ducks Unlimited | Maryland
Delaware
9. Identify to barriers to landowner willingness for agricultural landowners. | OpinionWorks and UMD Report | Wetland Workgroup | Pennsylvania | December 2015 | Funded by 2015 CBP GIT funding
|  | OpinionWorks and UMD | Maryland
CBT
10. Workshop at Delaware Wetland Conference to refine marketing and outreach strategies | More refined marketing and outreach recommendations to engage landowners | Wetland Workgroup | Watershed wide | March 2016 | TBD
11. Develop solutions to address barriers and improve outreach. | Identify priority areas and implement outreach | Wetland Workgroup and practitioners | All states | September 2017 | TBD
Total | [5 empty] | TBD
Management Approach 3: Increase our technical understanding of the factors influencing restoration success.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
12. Continue to include technical presentations at Wetland Workgroup meetings | Information exchange | Wetland Workgroup, other partners | CB Watershed | Ongoing | 0
Shared lessons learned
13. Conduct research to optimize nontidal wetland restoration designs | To be developed | USGS | Pocomoke River | 2016 -2017 | TBD |  | Funded by USGS
| Total |  |  |  |  | 0
Management Approach 4: Prioritize areas for wetland restoration.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
14. Coordinate with black duck workgroup | Incorporate priority areas for black ducks from Black Duck Workgroup | Wetland Workgroup, Black Duck Workgroup | Tidal MD and VA | June 2016 | 0
15. Identify areas where wetland restoration would greatly benefit water quality and habitat | Develop prioritization criteria | Wetland Workgroup, outside consultants | CB Watershed | 2 years; completed by September 2017 | 75000
Identify areas for each state and/or priority watershed
16. Identify opportunities to restore large wetland acreages. | Areas identified for each state and/or priority watersheds | Wetland Workgroup, outside consultants | CB Watershed | Completed in concert with water quality analysis | 75000
| Total |  |  |  |  | 150000
Management Approach 5: Expand the involvement of local stakeholders.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
17. STAC Workshop - "Enhancing Capacity" | framework for enhancing capacity | Wetland Workgroup, other partners | CB Watershed | TBD | TBD
| Total |  |  |  |  | TBD