## Sheet1
Topic | Description | Due Date
Historic Data Cleanup | Collection of BMP Historic data (1985-2013) with emphasis on 2000-2013. All years are needed. Reporting of complete, quality-assured BMP historic data (including wastewater) are an output of CBPO 2016 grants, as they were for 2015. | Next opportunity for data to be included in Phase 6 beta is submission by March 31, 2016. Final data must be provided by September 30, 2016
Point Source Data Project | Approval of LOE and schedule; receive monthly updates during the anticipated project duration | LOE and schedule approved by WWTWG by January 11 meeting
Biosolids | Form biosolids subgroup | Confirm subgroup membership in January 2016
| Finalize recommendations on adjustments to inputs (P solubility coefficient), conceptual model for biosolids application, and rule for forecasting and backcasting | To CBP modeling staff by April 1, 2016
| Biosolids data collection from jurisdictions (TN, TP, and lbs of biosolids) | Draft by June 30, 2016; final by September 30, 2016
Governance | Finalize signatory and at-large members | February 2016 confirmation of membership
RI, LMOS, Non-ag spray irrigation | Approval of memo on RI and Non-ag spray irrigation | Approved by WWTWG by April 1, 2016
| Develop and Approve memo for Large Monitored Onsite Systems | Approved by WWTWG by April 1, 2016
| Data collection from jurisdictions | Draft by June 30, 2016; final by September 30, 2016
Attenuation Panel | Approval of Attenuation Panel Report | Approved by WWTWG by April 5 meeting
Boat Pump Out | Approval of Boat Pump Out Panel Report | Approved by WWTWG by August 2 meeting
Onsite Systems Panel | Approval of Onsite Systems report | Approved by WWTWG by August 2 meeting.